## Phased Total Project Cost-BUILD
PROJECT ESTIMATE - KEEPING THE OLD LOCOMOTIVE SHOP FOR THE OPERATION AND MAINTENANCE SHOP | [10 empty] | 2018-07-01
PROJECT NAME………..…..UTA DEPOT DISTRICT TECHNOLOGY CENTER |  |  | Total Project Costs | Phase I- demo and stabilize Maint, West parking, retention pond & Breezeway demo | Phase II- Wash Bldg | Phase III- Diesel fueling | Phase IV- Bus Canopies & site work | Phase V- Maint and Admin/Ops. Bldg completion | Phase V A- Maint Bldg completion Subtotal | Phase V B- Admin/Ops. Bldg completion Subtotal | Phase VI- Photovoltaic Array (PV) and Micro Grid System
LOCATION…………...……..SALT LAKE CITY, UT
ARCHITECT…..……..…...…RNL DESIGN
STAGES OF DESIGN- 100% Contract Documents (CD) Phases
CSI # | DESCRIPTION |  | FY 2019 costs | FY 2019 costs | FY 2019 costs | FY 2019 costs | FY 2019 costs | FY 2019 costs | FY 2019 costs | FY 2019 costs | FY 2019 costs
BUILDING COST SUMMARY
02 | SITEWORK & DEMOLITION, incl. Sec. 31, 32, 33 |  | 7764779.0488 | 1672857.6 | 128180 | 0 | 1799492.7 | 2852388.7 | 2281910.96 | 570477.74 | See below
03 | CONCRETE |  | 3263821.9893 |  | 201488 |  |  | 2510911 | 2136276 | 374635
04 | MASONRY |  | 1346212.7537 |  | 163076 |  |  | 955694 | 902002 | 53692
05 | METALS |  | 2436895.731 |  | 13304 |  |  | 2011878 | 1231242 | 780636
06 | WOODS & PLASTICS |  | 406656.6788 |  | 0 |  |  | 337952 | 246677 | 91275
07 | THERMAL & MOISTURE PROTECTION |  | 3371153.6885 | 753182 | 55395 |  |  | 1993020 | 705779 | 1287241
08 | DOORS & WINDOWS |  | 2474296.613 |  | 114555 |  |  | 1941709 | 1316061 | 625648
09 | FINISHES |  | 1778926.8323 |  | 38152 |  |  | 1440225 | 650383 | 789842
10 | SPECIALTIES |  | 504771.1219 |  | 2408 |  |  | 417082 | 265602 | 151480
11 | EQUIPMENT - for M&O & Wash 100% see below |  | 1341350.2299 |  | 0 | 1109729 |  | 5000 | 0 | 5000
12 | FURNISHINGS |  | 44760.2474 |  | 0 |  |  | 37198 | 14774 | 22424
13 | SPECIAL CONSTRUCTION |  | 4256379.6938 |  | 0 |  | 3400603 | 136661 | 136661 | 0
14 | CONVEYING SYSTEMS |  | 96023.1127 |  | 0 |  |  | 79800 | 28875 | 50925
15 | MECHANICAL, incl.Sec. 21, 22, 23 |  | 4471860.1311 |  | 166847 |  |  | 3549492 | 2647227 | 902265
16 | ELECTRICAL, incl. Sec. 26, 27, 28 |  | 3621540.5729 |  | 116735 |  |  | 2892946 | 1963194 | 929752
| SUBTOTAL |  | 37179428.4452 | 2426039.6 | 1000140 | 1109729 | 5200095.7 | 21161956.7 | 14526663.96 | 6635292.74
| GENERAL CONDITIONS |  | 2078683.7955 | 182301.6963 | 50407 | 55930 | 290734.8262 | 1149475 | 841379 | 308096
| OVERHEAD & PROFIT |  | 1177743.9328 | 76850.3858 | 31516 | 34970 | 164724.9949 | 669344 | 476710 | 192634
| Maintenance Building Expansion Add Alt. & Add Alt. #1 |  | 3582484.4475 |  |  |  |  | 3249419 | 3249419 | 0
| Wash Building Expansion Additive or Deductive Alt. |  | 340432.155 |  | 308782
| Subtotal Alternates |  | 3922916.6025 | 0 | 308782 | 0 | 0 | 3249419 | 3249419 | 0 | 0
| TOTAL CONSTRUCTION COST |  | 44358772.8793 | 3231083.6297 | 1642475.5787 | 1444713.5538 | 6805313.9516 | 31235186.4801 | 22648430.6528 | 8586755.9238 | 0
SOFT COSTS
| Plan Check Fees |  | 180494.5727 | 13147.1864 | 6683.1859 | 5878.4979 | 27690.6268 | 127095.0757 | 92155.8131 | 34939.263 | 0
| Building Permit |  | 288741.9811 | 21031.9047 | 10691.2707 | 9403.9899 | 44297.4341 | 203317.3818 | 147424.1117 | 55893.2707 | 0
| 1% State Permit Fee |  | 2887.9132 | 210.355 | 106.931 | 94.056 | 443.05 | 2033.5212 | 1474.493 | 559.0282 | 0
| Utility Connection Fees and Impact Fees |  | 300824.2878 | 21911.9773 | 11138.6432 | 9797.4965 | 46151.0447 | 211825.1261 | 153593.0218 | 58232.1049 | 0
| Furniture Fixtures & Equipment |  | 842308.0057 | 0 | 0 | 0 | 0 | 842308.0057 | 620672.3323 | 221635.6735 | 0
| Owner Purchased Equipment |  | 6200520.4282 | 0 | 0 | 0 | 0 | 6200520.4282 | 6200520.4282 | 0 | 0
| A/E Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| A/E Construction Administration (Estimated) |  | 1383791.7237 | 351358.8921 | 51789.9565 | 44707.0121 | 0 | 935935.8753 | 689663.993 | 246271.8823 | 0
| Reimbursables |  | Inc. in A/E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Owner's Construction Contingency -10%/5% Onwer |  | 4931721.3859 | 359225.5396 | 182607.2128 | 160620.4188 | 756601.4553 | 3472666.7594 | 2518008.091 | 954658.6791 | 0
| Special Inspections & Testing |  | 443458.3189 | 112598.6093 | 16596.9247 | 14327.0812 | 0 | 299935.7076 | 221013.9211 | 78921.7864 | 0
| Energy Modeling |  | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E
| LEED Documentation A/E |  | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E | Inc. in A/E
| LEED Registration / Commissioning Fees |  | 96263.7721 | 0 | 0 | 0 | 0 | 96263.7721 | 96263.7721 | 0 | 0
| Contractor's LEED Certification Fees |  | 1773834.4788 | 0 | 0 | 0 | 0 | 1773834.4788 | 1773834.4788 | 0 | 0
| Lead Paint Abatement (Allowance) |  | 180494.5727 | 0 | 0 | 0 | 0 | 180494.5727 | 180494.5727 | 0 | 0
| Asbestos Abatement (Allowance) |  | 541483.718 | 0 | 0 | 0 | 0 | 541483.718 | 541483.718 | 0 | 0
| Contaminated Soils Abatement (Allowance) |  | 342939.6881 | 0 | 0 | 0 | 0 | 342939.6881 | 274351.7504 | 68587.9376 | 0
| Misc. Contamination Abatement (Allowance) |  | 60164.8576 | 0 | 0 | 0 | 0 | 60164.8576 | 60164.8576 | 0 | 0
| Unforeseen Below Grade Conditions (Allowance) |  | 601648.5755 | 0 | 0 | 0 | 0 | 601648.5755 | 481318.8604 | 120329.7151 | 0
| 1 MW Photovoltaic Array |  | 5013188.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5013188.6043
| Art |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL COST |  | 67543539.7634 | 4110568.094 | 1922089.7035 | 1689542.1061 | 7680497.5625 | 47127654.0237 | 36700868.8681 | 10426785.2646 | 5013188.6043
|  | UTA Admin Expenses | 1994308.7457 | 121369.74 | 56752.138 | 49885.875 | 226776.4384 | 1391503.7982 | 1083639.7331 | 307864.0683 | 148020.7561
|  | SubTotal | 69537848.5091 | 4231937.834 | 1978841.8414 | 1739427.9812 | 7907274.0009 | 48519157.8219 | 37784508.6012 | 10734649.3329 | 5161209.3604
|  | Remaining Hambline Relocation Expenses | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Project Cost | 70437848.5091 | 5131937.834 | 1978841.8414 | 1739427.9812 | 7907274.0009 | 48519157.8219 | 37784508.6012 | 10734649.3329 | 5161209.3604
|  | USE | 70500000 | 5200000 | 2000000 | 1700000 | 7900000 | 48500000 | 37800000 | 10800000 | 5200000